## Sheet1
System Name:Airline Management System
Members:Delima, Mangoroban, Canal
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. LOGIN | Allen |  |  | In-Progress
1.1. Creating UI | B | 2024-08-21 |  | DONE
1.2. Integrate with DB | B | 2024-08-22 |  | TODO
2. LOGOUT | C | 2024-08-20 |  | In-Progress
FEEDBACKFORM | Delima | 2024-09-30 |  | In-Progress
BOOKING |  |  |  | TODO
FLIGHTS |  |  |  | TODO
SIGN-UP | CANAL | 2024-09-30 |  | In-Progress
CUSTOMER SUPPORT |  |  |  | TODO
Tracking Status